## Backlog
ID | Parent | Task | Mod | System | Type | Priority | Status | Effort | Original section | Notes
T-001 |  | Operation to gather herbs automatically | GBO3 | Operations | Feature | P3 | Open |  | Unsorted
T-002 |  | Review no-stock aim penalty: no-stock SMGs struggle to out-aim pistols | GBO3 | Weapons | Balance | P2 | Open |  | Unsorted
T-003 |  | Overwatch against doors | AI Overhaul | AI Behavior | Feature | P2 | Open |  | AI new stuff
T-004 |  | Enemy leaving view should not reveal its position to the player | AI Overhaul | Visibility | Feature | P2 | Open |  | AI new stuff | Mod assignment uncertain (could be GBO3)
T-005 |  | AP check so autofire is selectable when merc can fire 2 bullets | GBO3 | Fire Modes | Feature | P2 | Done |  | Fire modes
T-006 |  | Maybe change HK receiver effect for clarity | GBO3 | Components | UX | P3 | Open |  | Fire modes
T-007 |  | Selective burst on HK21 and other MGs that have it | GBO3 | Fire Modes | Feature | P2 | Open |  | Fire modes
T-008 |  | MG description hints not showing ROF | GBO3 | UI & Descriptions | Bug | P2 | Done |  | Fire modes
T-009 |  | Recoil booster | GBO3 | Components | Feature | P2 | Done |  | Fire modes
T-010 |  | Adjust MG 58 RPM | GBO3 | Fire Modes | Balance | P2 | Done |  | Fire modes
T-011 |  | Investigate burst fire AP or RPM | GBO3 | Fire Modes | Investigation | P2 | Done |  | Fire modes
T-012 |  | Solve the AKSU reliability dilemma | GBO3 | Weapons | Balance | P2 | Open |  | Fire modes
T-013 |  | Better crit scaling for selective burst | GBO3 | Fire Modes | Balance | P2 | Done |  | Fire modes
T-014 |  | Psycho trait | GBO3 | Perks & Traits | Feature | P2 | Open |  | Fire modes | Scope not specified in original
T-015 |  | MG higher base AP cost? | GBO3 | AP Economy | Balance | P3 | Proposal |  | Fire modes
T-016 |  | Mouseover showing how many attacks fit at a position (stance, aim) given fractional AP | GBO3 | UI & Descriptions | UX | P2 | Open |  | UI
T-017 |  | Burst weapon AP shows a stale number | GBO3 | UI & Descriptions | Bug | P1 | Open |  | UI
T-018 |  | Show recoil delta on actions | GBO3 | UI & Descriptions | UX | P2 | Open |  | UI
T-019 |  | Caliber/ammo params in their own section (remove crit damage and base chance from hints) | GBO3 | UI & Descriptions | UX | P2 | Done |  | UI
T-020 |  | Scale aim in hints by merc and handgun status | GBO3 | UI & Descriptions | UX | P2 | Done |  | UI
T-021 |  | Pellet count in caliber section | GBO3 | UI & Descriptions | UX | P3 | Done |  | UI
T-022 |  | Further details include AP to swap and AP to reload | GBO3 | UI & Descriptions | UX | P3 | Done |  | UI
T-023 |  | Noise shown even when no ammo loaded | GBO3 | UI & Descriptions | Bug | P3 | Done |  | UI
T-024 |  | Bobby Ray's showing old crit scaling | GBO3 | UI & Descriptions | Bug | P2 | Done |  | UI
T-025 |  | Unified component handling with ancestor/CTH mode | GBO3 | Components | Refactor | P1 | Done |  | Housekeeping
T-026 | T-025 | ↳ Fix/unify with aCTH logic | GBO3 | Components | Refactor | P1 | Done |  | Housekeeping
T-027 | T-025 | ↳ Verify whether the patch called from ToG is redundant | GBO3 | Compatibility | Investigation | P2 | Done |  | Housekeeping | Not redundant: visual changes and foldable stock foldability
T-028 |  | Remove unused calibers from Bobby Ray's list | GBO3 | Loot & Economy | Content | P3 | Done |  | Housekeeping
T-029 |  | Check unjam skill mechanic; if flat, turn into a skill check | GBO3 | Weapons | Balance | P2 | Open |  | General
T-030 |  | Heavy rain aim penalty triggering indoors? | GBO3 | Accuracy | Investigation | P2 | Open |  | General
T-031 |  | Cumbersome stance AP not on new scale (description hints, display only) | GBO3 | AP Economy | Bug | P2 | Done |  | New AP scale
T-032 |  | Gas mask AP reduction not on new scale | GBO3 | AP Economy | Bug | P1 | Open |  | New AP scale
T-033 |  | AP calc can yield less than a 10 step | GBO3 | AP Economy | Refactor | P3 | Done |  | New AP scale
T-034 |  | Morale effects using old AP scale | GBO3 | AP Economy | Bug | P1 | Done |  | New AP scale
T-035 |  | Shipments: got a tier 3 MG after 2 fights | GBO3 | Loot & Economy | Balance | P2 | Done |  | Components
T-036 |  | Investigate and balance tier unlocking | GBO3 | Components | Balance | P2 | Open |  | Attachments
T-037 |  | Possibly rescale parts gained | GBO3 | Loot & Economy | Balance | P3 | Open |  | Attachments
T-038 |  | CUAE handling of attachments | GBO3 | Compatibility | Feature | P2 | Open |  | Attachments
T-039 |  | Spreadsheet for attachment costs | GBO3 | Components | Tooling/Docs | P3 | Open |  | Attachments
T-040 |  | Find a use for Lens and Chips | GBO3 | Loot & Economy | Feature | P1 | Open |  | Attachments | Marked !!! in original
T-041 |  | Component icons/models from ToC: 5.45, 7.62x54R, .45 ACP, .44 rifle suppressors, Mauser? | GBO3 | Components | Art/Content | P3 | Open |  | Attachments | Open question: guns that change calibers
T-042 |  | Caliber-changing barrels now block muzzle (no incompatibility) | GBO3 | Components | Feature | P2 | Done |  | Attachments
T-043 | T-042 | ↳ Custom logic for caliber-changing barrels | GBO3 | Components | Feature | P4 | Open |  | Attachments | Optional
T-044 |  | P90 was using 5.56 suppressor and compensator | GBO3 | Components | Bug | P3 | Done |  | Attachments | Removed from P90
T-045 |  | Change RS grading: compact -> assault compact -> assault/vulto | GBO3 | Components | Content | P2 | Done |  | Design
T-046 |  | Rename advanced RS for pistols | GBO3 | Components | Text | P3 | Open |  | Design
T-047 |  | Add compact Advanced (Glock RS) to rifles? | GBO3 | Components | Content | P3 | Proposal |  | Design
T-048 |  | Remove Vulto RS from pistols? | GBO3 | Components | Content | P3 | Proposal |  | Design
T-049 |  | Remove ToG handguards | GBO3 | Components | Content | P3 | Done |  | Design | RKs done
T-050 |  | No interchangeable stock between RKs | GBO3 | Components | Content | P3 | Done |  | Design
T-051 |  | Prune components that don't make sense (elegance first) | GBO3 | Components | Content | P2 | Open |  | Design
T-052 |  | ACOG +1 min aim level for aimed attacks? | GBO3 | Components | Balance | P3 | Proposal |  | Design
T-053 |  | Re-tune component AP cost for new AP scale | GBO3 | Components | Balance | P2 | Done |  | Design
T-054 | T-053 | ↳ Handgun barrels -> 3 | GBO3 | Components | Balance | P2 | Done |  | Design
T-055 | T-053 | ↳ Light stock -> 5 | GBO3 | Components | Balance | P2 | Done |  | Design
T-056 | T-053 | ↳ Heavy stock unchanged | GBO3 | Components | Balance | P2 | Done |  | Design
T-057 | T-053 | ↳ Barrels reduced | GBO3 | Components | Balance | P2 | Done |  | Design
T-058 |  | Rarity weight for components/attachments on Bobby Ray's | GBO3 | Loot & Economy | Feature | P2 | Done |  | Code/implementation
T-059 |  | Make components scrappable | GBO3 | Components | Feature | P2 | Done |  | Code/implementation
T-060 |  | Compensator per caliber | GBO3 | Components | Feature | P2 | Done |  | Code/implementation
T-061 |  | AK-74 bipod not using item | GBO3 | Components | Bug | P2 | Done |  | Code/implementation
T-062 |  | Scout suppressor: create one or use the 5.56 one | GBO3 | Components | Content | P3 | Open |  | Code/implementation
T-063 |  | Mag modification available even when RevMags is loaded | GBO3 | Compatibility | Bug | P2 | Done |  | Other (components)
T-064 |  | Mags visually bugged with RevMags | GBO3 | Compatibility | Bug | P2 | Done |  | Other (components)
T-065 |  | Folded stock AP reduction (M11 was bugged) | GBO3 | Components | Bug | P2 | Done |  | Other (components)
T-066 |  | SKS extended barrel wrong accuracy param | GBO3 | Components | Bug | P2 | Done |  | Other (components) | Original says 'Fixed???' - worth re-verifying
T-067 |  | Small threshold bonus for 1.5x scopes | GBO3 | Components | Balance | P3 | Done |  | Other (components)
T-068 |  | Change AP scale | GBO3 | AP Economy | Feature | P1 | Done |  | New mechanics intended
T-069 | T-068 | ↳ Smooth rotation cost | GBO3 | AP Economy | Feature | P1 | Done |  | New mechanics intended
T-070 | T-068 | ↳ Smooth dexterity scaling for manual cycling AP cost | GBO3 | AP Economy | Feature | P1 | Done |  | New mechanics intended
T-071 | T-070 | ↳ Retune manual cycling costs | GBO3 | AP Economy | Balance | P1 | Done |  | New mechanics intended
T-072 |  | Autofire shot count | GBO3 | Fire Modes | Feature | P1 | Done |  | New mechanics intended
T-073 |  | MG recoil/setup rework | GBO3 | Recoil | Feature | P1 | Needs testing |  | New mechanics intended | Original: 'needs further testing'
T-074 |  | Elliptical crouch/prone effect on aperture | GBO3 | Accuracy | Feature | P1 | Done |  | New mechanics intended
T-075 |  | Rotating while prone costs more after the initial angle | GBO3 | AP Economy | Feature | P3 | Open |  | New mechanics intended
T-076 |  | Safety mechanism so discontinued guns keep their patching (save safety) | ToG Patch | Compatibility | Feature | P1 | Done |  | ToG - Code
T-077 |  | Barry shaped charge too sensitive to alterations; increase angle | Explosive Overhaul | Explosives | Balance | P2 | Open |  | EO
T-078 |  | Shotgun pellets interaction with GunsHurt option | GBO3 | Shotguns | Investigation | P2 | Open |  | Other balancing
T-079 |  | Shotgun pellet balancing and spread (duckbill etc.) | GBO3 | Shotguns | Balance | P2 | Open |  | Other balancing
T-080 |  | Slug damage? | GBO3 | Shotguns | Balance | P3 | Open |  | Other balancing
T-081 |  | Overwatch tuning (minor) | GBO3 | Overwatch | Balance | P3 | Open |  | Other balancing | Ideas: costlier action, tighter OW cone, 3 aim levels
T-082 |  | Change Grizzly melee perk to recoil or other | GBO3 | Perks & Traits | Balance | P2 | Done |  | Other balancing
T-083 |  | Fix Shooting Stance animation, esp. mobile attack | GBO3 | Animation | Bug | P2 | Done |  | QOL
T-084 |  | Crosshair AP cost breakdown refactor (clearer stance AP display) | GBO3 | UI & Descriptions | UX | P2 | Done |  | QOL
T-085 |  | F1 in-game 'wiki' | GBO3 | UI & Descriptions | Feature | P3 | Open |  | QOL
T-086 |  | Take-cover grazing hits show as Fog in floating text | GBO3 | UI & Descriptions | Bug | P3 | Done |  | QOL
T-087 |  | Handling scaling to make merc accuracy less random / less enemy-biased | GBO3 | Accuracy | Balance | P3 | Open |  | aCTH fragilities | 'Maybe' in original
T-088 |  | Pellets (and maybe other projectiles) can hit the shooter at adjacent range | GBO3 | Accuracy | Bug | P1 | Open |  | aCTH fragilities | Marked Important; vector must not touch shooter
T-089 |  | Enemies try to shoot through the floor (run and gun) | GBO3 | Accuracy | Bug | P1 | Open |  | aCTH fragilities | Repro savegame exists
T-090 |  | Switching to old CTH doesn't update component Aim Acc already applied | GBO3 | Components | Bug | P2 | Done |  | aCTH fragilities
T-091 |  | Kalyna missed a shot in old-CTH overwatch but it hit? | GBO3 | Overwatch | Bug | P2 | Open |  | aCTH fragilities | Needs investigation
T-092 |  | Reflexes not affecting hipfire/snapshot in aCTH | GBO3 | Accuracy | Bug | P2 | Done |  | aCTH fragilities
T-093 |  | Verify graphic display of single-shot recoil; review burst too | GBO3 | Recoil | Investigation | P2 | Open |  | aCTH fragilities
T-094 |  | Prone overwatch vs hyenas had abysmal CTH at close range; no-LOS still triggers OW | GBO3 | Overwatch | Bug | P1 | Open |  | aCTH fragilities
T-095 |  | Make sure aCTH lite works as intended | GBO3 | Accuracy | QA | P1 | Open |  | aCTH fragilities | Bold in original
T-096 |  | Check behavior against non-humanoids | GBO3 | Accuracy | QA | P2 | Done |  | aCTH fragilities
T-097 |  | Ricochets still work? | GBO3 | Accuracy | QA | P2 | Done |  | aCTH fragilities
T-098 |  | Check ricochet damage reduction still applies | GBO3 | Accuracy | QA | P2 | Open |  | aCTH fragilities
T-099 |  | Aim in interrupt showed 0 levels | GBO3 | Accuracy | Bug | P2 | Done |  | aCTH fragilities
T-100 |  | Strange collision when shooting from above at very close range | GBO3 | Accuracy | Bug | P2 | Done |  | aCTH fragilities
T-101 |  | Shotgun: kill reported without any 'attack hit' striking the unit | GBO3 | Shotguns | Bug | P1 | Done |  | aCTH fragilities
T-102 |  | Out of breath impact on aim | GBO3 | Accuracy | Feature | P1 | Done |  | aCTH reimplementation
T-103 |  | AN-94 2-round burst | GBO3 | Fire Modes | Feature | P1 | Done |  | aCTH reimplementation
T-104 |  | Snipe/Pin Down action | GBO3 | Accuracy | Feature | P1 | Done |  | aCTH reimplementation
T-105 |  | Low profile CTH mod for crocs disabled in aCTH | GBO3 | Accuracy | Feature | P1 | Done |  | aCTH reimplementation
T-106 |  | Camouflage | GBO3 | Accuracy | Feature | P1 | Done |  | aCTH reimplementation
T-107 |  | Scopes with body-part / cover-bypass bonuses | GBO3 | Components | Feature | P1 | Done |  | aCTH reimplementation | Handzolt: more acc, worse snapshot
T-108 | T-107 | ↳ Thermal scope | GBO3 | Components | Feature | P2 | Open |  | aCTH reimplementation
T-109 |  | Gas, smoke and other grazing mechanics | GBO3 | Accuracy | Feature | P1 | Done |  | aCTH reimplementation
T-110 |  | Grizzly perk (recoil calc) | GBO3 | Perks & Traits | Feature | P1 | Done |  | aCTH reimplementation
T-111 |  | CQC bonus perk | GBO3 | Perks & Traits | Feature | P1 | Done |  | aCTH reimplementation
T-112 |  | Major perk (Bullet Hell) | GBO3 | Perks & Traits | Feature | P1 | Done |  | aCTH reimplementation
T-113 |  | Spiritual perk | GBO3 | Perks & Traits | Feature | P1 | Done |  | aCTH reimplementation
T-114 |  | MG Setup Get AP | GBO3 | AP Economy | Feature | P1 | Done |  | aCTH reimplementation | Ended up decreasing delta by 1
T-115 |  | Run and Gun recoil penalty modifier | GBO3 | Recoil | Feature | P1 | Done |  | aCTH reimplementation
T-116 |  | Scopes: make floor mul a readable effect (or revert to increased range) | GBO3 | Components | Balance | P2 | Open |  | aCTH balancing
T-117 |  | Off-part damage penalty only for the head? | GBO3 | Accuracy | Balance | P3 | Proposal |  | aCTH balancing
T-118 |  | Balance pass on scope accuracy numbers | GBO3 | Components | Balance | P2 | Open |  | aCTH balancing
T-119 |  | Digital Scope (G36) param handling in aCTH | GBO3 | Components | Feature | P2 | Open |  | aCTH balancing
T-120 |  | Remove stray from Get Cover action | GBO3 | Accuracy | Balance | P2 | Done |  | aCTH balancing
T-121 |  | Evaluate aim soft cap | GBO3 | Accuracy | Balance | P2 | Done |  | aCTH balancing | Cap is 70
T-122 |  | Pinned Down mod suppression for strays | GBO3 | Accuracy | Balance | P2 | Done |  | aCTH balancing
T-123 |  | Re-scale Aim Accuracy bonus for more gradient | GBO3 | Accuracy | Balance | P1 | Done |  | aCTH balancing
T-124 | T-123 | ↳ UV dot | GBO3 | Components | Balance | P2 | Done |  | aCTH balancing
T-125 | T-123 | ↳ No-stock penalty re-scale (more range vs more aim penalty) | GBO3 | Components | Balance | P2 | Done |  | aCTH balancing
T-126 | T-123 | ↳ Light stock | GBO3 | Components | Balance | P2 | Done |  | aCTH balancing
T-127 | T-123 | ↳ Match ammo | GBO3 | Components | Balance | P2 | Done |  | aCTH balancing
T-128 | T-123 | ↳ Grips (flat attack accuracy bonus) | GBO3 | Components | Balance | P2 | Done |  | aCTH balancing
T-129 | T-123 | ↳ Better handling of the component aim scaler | GBO3 | Components | Balance | P2 | Done |  | aCTH balancing
T-130 |  | Review handling-while-standing penalty | GBO3 | Accuracy | Balance | P2 | Done |  | aCTH balancing
T-131 | T-130 | ↳ Decide if recoil while standing uses the same params (weigth_held_mul) | GBO3 | Recoil | Balance | P2 | Done |  | aCTH balancing
T-132 |  | Lower status-effect chance for stray shots | GBO3 | Accuracy | Balance | P2 | Done |  | aCTH balancing
T-133 | T-132 | ↳ Pellets | GBO3 | Shotguns | Balance | P2 | Done |  | aCTH balancing
T-134 |  | Handgun extra hints show reduced aim acc | GBO3 | UI & Descriptions | Text | P2 | Done |  | aCTH descriptions
T-135 |  | Take-cover-not-grazing mod option | GBO3 | UI & Descriptions | Text | P2 | Done |  | aCTH descriptions
T-136 |  | Smoke not grazing; decide if LOS | GBO3 | UI & Descriptions | Text | P2 | Done |  | aCTH descriptions
T-137 |  | Recoil CTH UI display (still shows old -x% per shot) | GBO3 | UI & Descriptions | UX | P2 | Open |  | aCTH descriptions
T-138 |  | Snapshot not resetting on same target (page description only) | GBO3 | UI & Descriptions | Text | P3 | Open |  | aCTH descriptions
T-139 |  | DualShot max aim = 3 instead of 1 | GBO3 | UI & Descriptions | Text | P2 | Done |  | aCTH descriptions
T-140 |  | Autofire max aim levels no longer 1 | GBO3 | UI & Descriptions | Text | P2 | Done |  | aCTH descriptions
T-141 |  | Burst shots no longer lose aim bonus | GBO3 | UI & Descriptions | Text | P2 | Done |  | aCTH descriptions
T-142 |  | Camouflage effect | GBO3 | UI & Descriptions | Text | P2 | Done |  | aCTH descriptions
T-143 |  | MG Setup / set-up bonuses (bonus is on being prone now) | GBO3 | UI & Descriptions | Text | P2 | Done |  | aCTH descriptions
T-144 |  | aCTH CTH UI: separate final-accuracy line (aperture vs target size); modifiers as 1.2x not 120% | GBO3 | UI & Descriptions | UX | P2 | Open |  | aCTH descriptions | Original sentence is cut off ('and they should')
T-145 |  | No stat boost in hyena or melee overhaul? | AI Overhaul | AI Behavior | Balance | P3 | Proposal |  | AI Overhaul
T-146 |  | Militia custom AI: stay close, defensive | AI Overhaul | AI Behavior | Feature | P3 | Open |  | AI Overhaul
T-147 |  | Hyenas and other animals unaware of overwatch | AI Overhaul | AI Behavior | Feature | P2 | Open |  | AI Overhaul
T-148 |  | Grenade decision: avoid when very close to another target | AI Overhaul | AI Behavior | Feature | P2 | Open |  | AI Overhaul
T-149 |  | Check pellet pre-calc damage rationale | AI Overhaul | AI Behavior | Investigation | P2 | Open |  | AI Overhaul
T-150 |  | Buckshot should not degrade to single shot | AI Overhaul | AI Behavior | Bug | P2 | Done |  | AI Overhaul
T-151 |  | Mechanics check | AI Overhaul | AI Behavior | QA | P2 | Done |  | AI Overhaul
T-152 |  | aCTH: aim for the head if it's the only part out of cover | AI Overhaul | AI Behavior | Feature | P2 | Open |  | AI Overhaul
T-153 |  | Enemy LastPos generates threat; enemies chase it | AI Overhaul | AI Behavior | Feature | P1 | Done |  | AI Overhaul
T-154 |  | Check grenade distribution (more timed grenades) | AI Overhaul | Loot & Economy | Balance | P2 | Done |  | AI Overhaul
T-155 |  | Check AI recoil calc in aCTH | AI Overhaul | AI Behavior | QA | P2 | Done |  | AI Overhaul
T-156 |  | AI shooting prone behind tiny cover it can't hit through | AI Overhaul | AI Behavior | Bug | P1 | Done |  | AI Overhaul | Follow-up: confirm they don't lose turns
T-157 |  | Tune Threat Exposure, possibly simplify | AI Overhaul | AI Behavior | Balance | P2 | Done |  | AI Overhaul
T-158 | T-157 | ↳ Fix LOS | AI Overhaul | AI Behavior | Bug | P2 | Done |  | AI Overhaul
T-159 | T-157 | ↳ Fix debug overlay not decomposing ready curve | AI Overhaul | AI Behavior | Tooling/Docs | P3 | Done |  | AI Overhaul
T-160 |  | Smoke usage | AI Overhaul | AI Behavior | Feature | P2 | Open |  | AI Overhaul new stuff
T-161 |  | Bandage usage | AI Overhaul | AI Behavior | Feature | P2 | Open |  | AI Overhaul new stuff
T-162 |  | Overwatch / grenades at last target pos when unit is hidden (esp. rooftops) | AI Overhaul | AI Behavior | Feature | P2 | Open |  | AI Overhaul new stuff
T-163 |  | Use Take Cover action more | AI Overhaul | AI Behavior | Feature | P3 | Open |  | AI Overhaul low priority
T-164 |  | Don't shoot through walls (esp. aCTH) | AI Overhaul | AI Behavior | Bug | P3 | Open |  | AI Overhaul low priority
T-165 |  | Under Pin Down, ignore it if the attack is unlikely to hit | AI Overhaul | AI Behavior | Feature | P3 | Open |  | AI Overhaul low priority
T-166 |  | 'Impatience': more aggressive when neither being shot nor hitting | AI Overhaul | AI Behavior | Feature | P3 | Open |  | AI Overhaul low priority
T-167 |  | Groups more aggressive? | AI Overhaul | AI Behavior | Balance | P3 | Proposal |  | AI Overhaul low priority
T-168 |  | Pin Down action | AI Overhaul | AI Behavior | Feature | P3 | Disabled |  | AI Overhaul low priority | Disabled for now
T-169 |  | Team strategy: autoweapons suppress, skirmishers close in | AI Overhaul | AI Behavior | Feature | P3 | Open |  | AI Overhaul low priority
T-170 |  | Stealth | AI Overhaul | AI Behavior | Feature | P4 | Open |  | AI Overhaul luxury
T-171 |  | Out-of-sight score when flanking | AI Overhaul | AI Behavior | Feature | P4 | Open |  | AI Overhaul luxury
T-172 |  | Unify all crits into Crit Scaling (per aim, HEC-based) | GBO3 | Accuracy | Feature | P2 | Done |  | New mechanics (luxury)
T-173 |  | Bonus crit per aim only on first burst shot? | GBO3 | Fire Modes | Balance | P4 | Proposal |  | New mechanics (luxury)
T-174 |  | MGs and bipods set up on cover/crouch | GBO3 | Recoil | Feature | P4 | Open |  | New mechanics (luxury)
T-175 |  | Vision cones / directional vision (AI must account for it) | GBO3 | Visibility | Feature | P4 | Open |  | New mechanics (luxury) | 'MEGA LUXURY'; cross-mod with AI Overhaul
T-176 |  | Agility defense against melee | GBO3 | Perks & Traits | Feature | P4 | Open |  | New mechanics (luxury)
T-177 |  | Rare calibers distribution (if kept) | GBO3 | Loot & Economy | Balance | P4 | Open |  | Low priority

## Summary
By priority
Priority | Open | Proposal | Needs testing | Disabled | Done | Total | Open %
P1
P2
P3
P4
Total
By type
Type | Open | Proposal | Needs testing | Disabled | Done | Total | Open %
Bug
Feature
Balance
UX
Text
Investigation
QA
Refactor
Content
Art/Content
Tooling/Docs
Total
By mod
Mod | Open | Proposal | Needs testing | Disabled | Done | Total | Open %
GBO3
AI Overhaul
Explosive Overhaul
ToG Patch
Total
By system
System | Open | Proposal | Needs testing | Disabled | Done | Total | Open %
AI Behavior
AP Economy
Accuracy
Animation
Compatibility
Components
Explosives
Fire Modes
Loot & Economy
Operations
Overwatch
Perks & Traits
Recoil
Shotguns
UI & Descriptions
Visibility
Weapons
Total
Open % counts Open + Proposal + Needs testing (columns B:D).

## Legend
Field | Value | Meaning
Priority | P1 | Must: blocks correctness/release, or flagged important/!!! in the original list
| P2 | Should: core to the mod's direction
| P3 | Could: nice to have, minor, or marked low priority
| P4 | Won't now / wishlist: marked luxury or low priority
Type | Bug | Behaves wrong vs. intended design
| Feature | New mechanic, action, or behavior
| Balance | Tuning numbers/curves of existing mechanics
| UX | Information display / interaction clarity
| Text | Description/hint wording only
| Investigation | Unknown cause or open question; outcome is a finding
| QA | Verify an existing system still works
| Refactor | Code structure, no intended gameplay change
| Content | Adding/removing/renaming presets (components, calibers)
| Art/Content | Icons, models
| Tooling/Docs | Spreadsheets, debug overlays, internal docs
Status | Open | Not started / in progress
| Proposal | Idea marked '?' in the original; needs a design decision first
| Needs testing | Implemented but flagged for more testing
| Disabled | Implemented but turned off
| Done | Checked in the original list
Effort | XS-XL | Yellow cells: left blank for you to fill
Parent | T-xxx | Sub-task of that ID (indented with ↳ in Task)
Note |  | Priority, Type and System were assigned by Claude from the wording; treat as a first pass.